## Work Sheet
WORK SHEET FOR HMS PROJECT
Team Member | Module | Task | Current Status(%) | Duration(Days)
Duminda Basnayaka | Authentication | Custom Login Page | 100% | 2
|  | Set Priviledges | 100% | 3
| Ward | Add/Edit/Delete/View | 100% | 2
| Bed | Add/Edit/Delete/View | 100% | 2
| Testing |  | 100% | 2 | 11
Yohan S. Wijesinghe | Nurse | Add/Edit/Delete | 80% | 2
| Medical Test | Add/Edit/Delete | 80% | 2
| Invoice | add/Handle related data | 85% | 4
| Testing |  | 10% | 2 | 10
Neranjan Mendis | Doctor | Add/Edit/Delete | 90% | 2
| Doctor Recommendation | Assign | 90% | 2
| Allocate Medical Test | Add/Edit | 90% | 2
| Testing |  | 90% | 2 | 8
Piyumi Atulugama | Patient | Add/Edit/Delete | 85% | 5
| Feedback | Add | 35% | 2
| Testing |  |  | 2 | 9
overall contribution | Intregrate system, Set up SVN for the project, |  |  | 3 | 3

## Progress Status
# Progress Status
Neranjan | 2015-02-11 | 2015-02-12 | 2015-02-13 | 2015-02-16 | 2015-02-17 | 2015-02-18 | 2015-02-19 | 2015-02-20 | 2015-02-23 | 2015-02-24 | 2015-02-25 | 2015-02-26 | 2015-02-27
Task | Manage data with databases | Create Business Logic for Doctor - 20% | Continuing With The Implementation Of Doctor - 40% | Continuing With The Implementation Of Doctor - 60% | Continuing With The Implementation Of Doctor - 75% | Continuing With The Implementation Of Doctor - 80% | Continuing With The Implementation Of Doctor - 85% | Continuing With The Implementation Of Doctor And UnitTesting | Continuing With The Implementation Of Doctor And Unit Testing | Continuing With The Implementation Of Doctor And Unit Testing | Designing pages and validation | Designing pages and validation | Designing pages and validation
Duminda
Task : | Manage data with databases | CPU is down.No works today | User Role Registartion and User registration is completed | User Login is implementing - 50% | User Login is completed- 50% ,Ward,Bed is completed 80% | add Customer Error Page/ Errorpage | Set Priviledges User Wice,Created common enum classes,Add Using block | Create a method for common exception handling for the project. | Add exception context for all methods.Resolved some bugs in user authentication | Implementation of ward and bed modules | Implementation of user and user roles modules | Adding regions,implementation of on successful messages | Commenting and renaming views
Piyumi
Task : | Manage data with databases | Create Business Logic for Invoice, Medical | Patient Insert/Update/Delete/Details | PatientadmissionDeatils Insert-75% | PatientadmissionDeatils delete/update/details-60% | Continuing with the impletation of PatientAdmissionDetails-70% | Continuing with the impletation of PatientAdmissionDetails-80%, Implement Feedback - 15% | Continuing with the impletation of PatientAdmissionDetails-85%, Implement Feedback - 25% | continuing implementing feedback-35% | continuing implementing feedback-55% | continuing implementing feedback-75% | continuing implementing feedback-85% | Add comment and validation
Yohan
Task : | Manage data with databases | Create Business Logic for nurse, | Create Business Logic for Invoice, Medical | Create UI for Invoice, Medical | Continuing With The Implementation Of Invoice-40% | Continuing With The Implementation Of Invoice-70% | add using block, and validate method in inovoice, Nurse, Medical test | add log4net for the business layer/ validate nurse and invoices | Error handling for the Invoices, Nurse, Medical Test | Create Patient Medical Test -50% | Create Patient Medical Test -70% | Create Patient Medical Test -80% | confirm message add for invoices, medical test, nurses, patient medical test